## Slide 1: Technologies for Radio Astronomy
CSIRO Astronomy and Space Science
Tasso Tzioumis
Facilities Program Director – Technologies
November 2016

## Slide 2
(Update since last ATUC meeting) - Review
Broad directions largely unchanged (Nov 2016)
ASKAP & SKA: Core business of the Engineering Program.
      Most of the program’s people and effort at present.
Development projects for all ATNF facilities. Budget??
Strategic developments – develop capabilities.
External contracts – maintain capabilities.
      FAST 19-beam system high priority in the last 6 months.
Directions for ATNF Engineering

## Slide 3
Available resources & allocations
FY 2016-17: ~50 FTEs!! (includes Workshop+Store ~7 FTE)
 Current allocations:
  ASKAP : ~ 15FTE  Ongoing commitment
      ASKAP production  Secondments (2); Terms and casuals (4)
        Nominally finish end 2016. Mostly extended by ~6 months.
  SKA: ~ 12 FTE  CSP ; Dish; AIV; PAF
    + additional ~2-3 FTE internal for PAF developments
  FAST: ~ 5 FTE (finish system End 2016!!) + Workshop time
  UWB: ~5 FTE (primarily in 2017) – after FAST ends
  Other projects: ~ 5 FTE (PAF@Parkes; Rocket PAF; RFoF; Ops support; …)
New recruits (replacing resigned or retired)
  1 Digital engineer (started end’Oct 2016)
  1 Mechanical engineer (starting Jan’2017)

## Slide 4
CABB (unchanged since Jun2016)
Formal CSIRO commitment to new functionality ceased Sept 2014
  Now ALL tasks covered by post-retirement fellows!!
  Adequate spares for operations and short-term support.
  Unlikely that 16 MHz would be completed!
  ATCA CABB upgrade?: GPU cluster based
    Leverage on GPU developments at Parkes
      Software correlation would allow unlimited zooms?
    Digital systems from UWB and SKA developments
    Hardware: ~$0.5M for replacing CABB
      Scalable for more bandwidth.
    >~$1M+ for realistic project
    External funding!!  Priority??

## Slide 5: FAST 19-beam Receiver - Status
Receiver system for FAST 500m telescope
Contract with NAOC
  Contract delivery by Feb 2017
  Try to complete within 2016
Mechanical parts (Dewar; Feed horns; OMTs)
  Construction completed
  Testing in RF range completed.
  Integration and cooling in Nov
Low noise amplifiers (LNAs)
  In production
RF “warm” electronics – Control and Monitor
  Designs finalised; Production started
  To be completed in 2016
2nd milestone - testing report on feeds  Invoice; This week!!
Construction to be completed by end’2016
Integration & Testing – may extend to January.
Shipping and Installation – early 2017
Photo credit: Wheeler Studios

## Slide 6: Ultra-wideband (UWB) for Parkes - summary
Observed band 700 - 4000 MHz; Tsys < 20K over most of band
ARC LIEF grant: $370k awarded for 2015 ~40% of direct costs
Institutions: CSIRO, Curtin, MPIfR, Melbourne, Monash, NAO/CAS, Swinburne, Sydney, Western Australia
    Contribute ~ 60% of direct costs
    CSIRO in-kind ~9 FTE total (over ~2-3 years)
Lead Institution is Swinburne. Managing external funds.
    Collaboration agreement signed June 2015
    Project plan in place – October 2015  Funds available
    BUT: Slow-down in delivery due to commitments to ASKAP, SKA, FAST.

## Slide 7: Parkes UltaWideBand system (UWB) - status
Band 700 – 4000 MHz; Tsys <20K
Consortium funding + ARC + CASS (labour)
Prototype feed built and design verified
  Patent and Publication
Cooled Rx version to be built in 2017
LNAs designed – foundry run underway (Dec’16)
Sampler/digitiser and timing (Back-end)
  Fully prototyped and tested
  Limited (4 channel) production – to be used with older Parkes receivers – March’17
  Full production run in 2017
Ethernet switch and GPU cluster – Ready!!
  Bought in early 2016 & used by PAF@ Parkes
  Software needed – Pulsars via Swinburne
    Other: Spectrometry,… - Need to develop.
RFI mitigation built-in – reference antenna
Full construction – 1st half of 2017
Installation – mid- 2017
Commissioning – 2nd half of 2017
Credit: Alex Dunning

## Slide 8
ADE PAF system for MPIfR  Parkes
Contract for standard ASKAP PAF for Effelsberg telescope.
RFI environment at Effelsberg & Parkes  mods to PAF filtering
  Funded by MPIfR
Modified beamformer outputs  Ethernet output
  Strategic use of PAF. Single-dish demonstration  Bonn PAF at Parkes
Commissioning/Early science
Collaborative Project:
  CASS- MPIfR
  Open to community. NOT NF
  Proposals Dec15 for APR2016
    Must bring resources
  FRBs – primary targets
  PAF to Bonn in Oct 2016

## Slide 9
Install/Commission: Planned for OCT2015 semester
      Bonn PAF filter modifications – Dec 2015  Done in Jan 2016
      Test digital/GPU system in Sydney – Dec 2015 ✔
    Parkes preparations: Early in semester
      Fibre wiring ~ 2 week shutdown: Started 23/11/15!! ✔
      Racks mods; Install GPUs and Back-end – Jan 2016 ✔ (end)
      PAF Install: 8-17 Feb 2016. Replace MB system for ~8 months. ✔
      Control computer via TOSS. Jan 2016 ✔
      Engineering Commissioning: Feb-Mar 2016 ✔
        Extensive beamforming tests and developments. ✔
2-3 engineers/scientists external support
      Germany and Jodrell Bank – 3 MPIfR engineer visit – Dec & Feb ✔
      Joint CSIRO/MPIfR post-doc – Started 1 Nov 2015 (full time) ✔
  Science Commission & Scientific Observations: APR2016 semester
    Ethernet Firmware mods – end March & continued support ✔
    Software by Bonn & Jodrell Bank: Protracted Commissioning!
  PAF to Bonn after Oct 2016 – Un-installed Nov’17 ✔
  Results – see talk by Aaron Chippendale
Bonn PAF at Parkes –Timelines

## Slide 10
PAF R&D under SKA-survey
    Continues as an Advanced Instrumentation Program (AIP)
      Pre-construction AIP consortium at next SKA Board meeting
      As Observatory Development Program (ODP) in SKA construction phase
  Key technology for CASS – world leader!  “Rocket” PAF (Alex Dunning)
PAF R&D - the “Rocket” PAF
Complete picture of the 5×4 test PAF array with the new “rocket” design, where the new central and edge element designs are visible.
more amenable to cryo cooling
 Cryo PAF system with <20K Tsys!!
Superb for single-dish large telescopes!
Cooled PAF for Parkes??
  ~$2M+. Funding??
  See Parkes talk by Jimi Green.

## Slide 11
Rocket PAF performance (5x4 prototype)

## Slide 12
SKA PAF Consortium
The SKA Organisation has agreed to set up a PAF Consortium as an Observatory Development Programme (ODP)
The PAF Consortium aims to:
  continue existing room-temp & cryo PAF development to establish a performance benchmark in mid-2018,
  develop requirements and performance metrics for SKA PAFs,
  establish science & business cases to support further PAF development and deployment of PAFs as a test array (TBC) prior to SKA Stage 2 construction.
Consortium partners include CSIRO (lead), ASTRON, JBO, INAF, OSO, JLRAT & MPIfR.

## Slide 13
SKA Construction/Verification/Commissioning. Start??
      Expect key Australian role. CASS in CSP-Low – follow-up
  ASKAP enhancements
    Tied-array: In ASKAP specs but NOT funded!
      Expert group report. ~$400k + 5.5 FTE (Firmware+Software)
    Transients: (Cf CRAFT)
      Add transient mode. Firmware only. ~5FTE effort. NOT Commensal.
  ASKAP upgrades. (mainly sensitivity improvements)
    “Transparent” legs. Reduce scatter. Improve Tsys by 10-20K.
      Initial investigations now. See talk by Keith! **
      Estimated cost ~$1.5M h/w + Labour!! Funding?
    “Skirts”: Reduce spillover. Better illumination. ~10K to Tsys?
    New PAFs (keep back-end) e.g. “Rocket” PAF.
      ~15K in Tsys + Better illumination. BUT many $$M?
  Air shower detection by ASKAP (Ekers proposal..)
Future technical Projects (2018+)
SKA & ASKAP

## Slide 14
N.B: Most single-dish cryo systems cost >$2M!!
UWB high (4-25 GHz) for Parkes. Considered in ATUC before.
    Leverage on SKA & UWB(low); use UWB GPU cluster & software
    ~$1.5-2M; timeline ~2-3 years; Priority??
    External funds – AAL; LIEF; Collaborators – overseas?
External contracts: Maintain/develop capabilities. Strategic.
    Present UWB systems. Strong interest from collaborators!
      2-3 contracts in 2017+ timescale?
    PAFs
      Current generation to Jodrell Bank. Contract executed. Funds received.
      Cryo PAFs for large singe-dishes. ~20K Tsys
        1st system for Parkes. Collaborative funding. Start in 2017-18?
        Good external candidates (MPIfR; JB; FAST; ….)
Future Projects & External Contracts

## Slide 15
SKA R&D
    SKA PAF test array. Up to 4 antennas. Under ODP?
    Rocket PAF  Cryo PAF systems . <20K Tsys
    Higher frequency PAFs: SKA; Arrays; Single-dish
    mm PAFs e.g. for ALMA (cf NRAO)
    Dual band PAFs
    MMIC packaging
16-25 GHz PAF on ATCA. Transformative for surveys!?
    Collaborative effort? E.g. SRT?
Aperture array applications:
    SETI; Array of PAFs; Needs Massive digital and GPU resources.
    Filled aperture array at ~100 MHz. All sky coverage.
Other technologies
  RF-over-fiber developments
  UWB in other bands
  Signal processing FPGA platforms
  Signal processing - GPUs
Future technical Projects (2018+)
PAFs & Others

## Slide 16
CASS Engineering/Technologies: (from ATSC presentation)
      World-class radio-astronomy instrumentation
      Pioneering cutting-edge technologies: PAF; UWB; DSP; RFoF
        For world-wide radio-astronomy facilities
      International reputation – Key player in SKA
  --> MUST maintain/enhance/develop
Issues for ATUC??
    Feedback on Scientific Priorities / Choices  Funding?
      ASKAP tied array mode
      ASKAP “upgrades”: e.g. transparent legs (~10K Tsys improvement?)
      UWB “high” at Parkes (4-25 GHz)?
      ATCA CABB upgrades? – GPUs; more BW; …
      Future PAF systems, beyond cryo-PAF@Parkes; e.g. 20 GHz PAF?
      Low-freq arrays; Aperture arrays; ??
      ….
Summary

## Slide 17: Thank you
Astronomy & Space Science
  Tasso Tzioumis
    t +61 2 9372 4350
    E Tasso.Tzioumis@csiro.au
    w www.csiro.au/cass