## Slide 1: BIGCAT
Chris Phillips | BIGCAT Project Lead
8th November 2021
CSIRO Astronomy and Space science
ATUC Open Session April 4, 2022

## Slide 2: ATCA-BIGCAT upgrade
BIGCAT: Broadband Integrated Gpu Correlator for ATca
  Replacement of CABB digitisers and correlator with a hybrid FPGA+GPU backend
LIEF funded, lead by WSU (PI Ray Norris)
Key aspects of BIGCAT:
  Double instantaneous bandwidth to ~8 GHz
  Flexible spectral resolution
  Improved reliability
  More flexibility:
    Many more options wrt. frequency resolution and integration times
    Ability to change quickly between different observing modes
  More adaptable to automated observing (e.g. rapid ToO follow-up)
  Retain standard CABB features (e.g. mosaicing)

## Slide 3: ATCA-BIGCAT signal chain
https://www.atnf.csiro.au/research/bigcat/BIGCAT_Overview.pdf
Notes: Show diagram of CABB – what elements are changing for BIGCAT (i.e. practically all of it except the antennas/receivers)
Key points here:
Note jimble will be common digitizer between Parkes and ATCA (cryoPAF)

## Slide 4: Status Update
Feedback on Scientific Requirements incorporated
  Delay in re-distribution because of COVID
Work on caobs underway to support software based correlation
  Will remove overheads such 3 cycle scan startup
  Eventual support of subarrays and other new modes
Design of GPU correlator well progressed
RF upgrade delayed due to contention between projects
  CABB Jimble replacement will occur before bandwidth upgrade
Jimble design progressing but delay with hardware design
  PLL chip not satisfactory, different chip needed and re-spin of prototype hardware
CABB Zoom issues – see Jamie’s talk
Planning on using (A)SDM for output – with Miriad/CASA support

## Slide 5: BIGCAT Timelines DRAFT TBC
Jimble production now September/October 2022
  No way of bringing forward
Jimble installation Feb 2023 (CABB Replacement)
  1 month installation
  2 month commissioning/shared risk
  Some modes (e.g. pulsar binning) unlikely to be initially available
    Don’t fear the CABB Zoom mode rollout problems!
RF upgrade delayed till mid 2024
  Contention with other projects for RF team members

## Slide 6: Feedback and questions:
BIGCAT Overview: https://www.atnf.csiro.au/research/bigcat/BIGCAT_Overview.pdf
BIGCAT Requirements: https://www.atnf.csiro.au/research/bigcat/bigcat_techreq.pdf
  Elizabeth Mahony BIGCAT Project Scientist
    Elizabeth.Mahony@csiro.au
    (On Leave)
  Chris Phillips BIGCAT Project Leader
    Chris.Phillips@csiro.au
  Jamie Stevens ATCA Systems Scientist
    Jamie.Stevens@csiro.au

## Slide 7: Thank you
Space and Astronomy
  Chris Phillips BIGCAT Project Leader
    +61 2 9273 4608
    Chris.Phillips@csiro.au